## 1) Two-Page Donor Concept Note (GCF/World Bank Style)

### Project Title

ClimateFunds Watch Mauritius: Strengthening Transparency, Accountability, and Community Oversight of Climate Adaptation Finance

### Country

Mauritius

### Duration

12 months (pilot + scale-up readiness)

### Funding Requested

USD 550,000

### Implementing Modality

Government-led implementation with local councils, civil society, and technical delivery partner(s)

### A. Context and Problem Statement

Mauritius faces escalating climate risks, notably flash floods and cyclones, with significant economic and social impacts. While domestic and international climate finance flows are increasing, delivery effectiveness is constrained by governance and implementation gaps, including:

- Incomplete transparency on allocation and expenditure of climate funds

- Weak project-level monitoring and fragmented reporting

- Limited citizen and local authority participation in oversight

- Elevated risk of misuse, delays, and “greenwashing”

- Insufficient digital tools and technical capacity for finance tracking

- Gaps in integrated climate and implementation data for decision-making

These bottlenecks reduce the speed and equity of adaptation delivery and undermine trust in public climate spending.

### B. Project Goal and Theory of Change

Goal: Improve the governance and impact of climate adaptation finance in Mauritius through digital transparency, participatory monitoring, and institutional accountability.

Theory of Change:
If Mauritius deploys a shared digital platform that links project data, budget flow, community reporting, and whistleblower-safe case management—while building local institutional capacity—then climate finance can be better tracked, bottlenecks identified earlier, and corrective action taken faster, resulting in improved adaptation outcomes for vulnerable communities.

### C. Objectives (12 months)

- Establish a public digital registry of adaptation projects and budgets in pilot councils.

- Enable near-real-time tracking of project milestones and disbursement-to-spending progress.

- Operationalize citizen feedback channels with geo-tagged evidence submission.

- Introduce confidential reporting and case-tracking workflows for integrity risks.

- Strengthen local-national coordination through shared dashboards and alert systems.

- Produce periodic public transparency outputs for accountability and learning.

### D. Components and Activities

Component 1: Climate Finance Transparency Portal

- Project registry (location, budget, contractor, timeline, status)

- Budget flow module (approved/disbursed/spent)

- Public map and downloadable transparency reports

Component 2: Community Monitoring

- Mobile/web reporting (photo/video + geotag)

- Structured categories (delays, quality issues, misuse, risk hotspots)

- Community verification and severity-based escalation

Component 3: Integrity & Whistleblower Module

- Anonymous/identified reporting channels

- Case tracking code and workflow status updates

- Confidential access controls and SOPs

Component 4: Local Authority Decision Support

- Council dashboard for project performance

- Delay/stall alerts and escalation pipeline

- Priority views for urgent resilience interventions

Component 5: Capacity Building and Governance

- Training for officials, handlers, and community monitors

- Data quality protocols and governance charter

- Joint review forums across ministries, councils, and CSOs

### E. Expected Results

Outputs

- Operational digital platform in two pilot councils

- Published climate project and budget data

- Functional citizen and whistleblower channels

- Trained public officers and community monitors

- Quarterly transparency bulletins and pilot learning report

Outcomes

- Increased visibility and traceability of climate finance

- Reduced response time to implementation bottlenecks

- Improved local participation in adaptation oversight

- Strengthened institutional accountability and trust

### F. Monitoring, Evaluation and Learning (MEL)

Key indicators:

- % adaptation projects publicly listed in pilot areas

- % projects with complete budget traceability

# citizen reports submitted / verified / resolved

- Median response time from report submission to action

# integrity cases processed with documented status updates

- % delayed projects identified and escalated within SLA

- Active users by stakeholder category

A baseline, midterm review, and endline assessment will capture progress and lessons for national scale-up.

### G. Budget Summary (USD, indicative)

- Digital platform development and UX: 220,000

- Integration, cybersecurity, hosting: 90,000

- Capacity building and stakeholder engagement: 80,000

- Pilot operations (2 councils): 70,000

- MEL and knowledge products: 40,000

- Project management and contingency: 50,000

Total: USD 550,000

### H. Risk Management

- Data quality risks: mandatory templates + validation rules

- Institutional resistance: co-design and formal governance roles

- Abuse of reporting channels: moderation and verification protocols

- Confidentiality concerns: encryption, role-based access, handler training

- Low uptake: local-language outreach and civil society partnerships

### I. Sustainability and Scale

The project is designed for institutional uptake through government ownership, council-level capacity transfer, and integration into routine reporting cycles. A scale-up roadmap will be prepared for national rollout and potential adaptation across SIDS contexts.